## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Milestone: Purchase & Installed Tablets at North and Downtown Location |  | 2024-01-01 | 2024-01-19 | 18 | bar: WEEK 1 M to WEEK 3 F
Select Tablet Vendor |  | 2024-01-01 | 2024-01-02 | 1 | bar: WEEK 1 M to WEEK 1 T
Create contract and statement of work for vendor |  | 2024-01-03 | 2024-01-04 | 1 | bar: WEEK 1 W to WEEK 1 T
Select table type that is ideal for tablets |  | 2024-01-05 | 2024-01-08 | 3 | bar: WEEK 1 F to WEEK 2 M
Select branding and designing package for tablets |  | 2024-01-09 | 2024-01-11 | 2 | bar: WEEK 2 T to WEEK 2 T
Update menu interface to match Sauce & Spoon branding layout |  | 2024-01-12 | 2024-01-15 | 3 | bar: WEEK 2 F to WEEK 3 M
Design mockup and upload software on tablets |  | 2024-01-16 | 2024-01-18 | 2 | bar: WEEK 3 T to WEEK 3 T
Tablets shipping and delivery |  | 2024-01-19 | 2024-01-19 | 0 | bar: WEEK 3 F
Milestone: Test tablets at North & Downtown Restaurant |  | 2024-01-22 | 2024-02-08 | 17 | bar: WEEK 4 M to WEEK 6 T
Upgrade POS system at North & Downtown restaurant |  | 2024-01-22 | 2024-01-24 | 2 | bar: WEEK 4 M to WEEK 4 W
Integrate POS system with tablets |  | 2024-01-25 | 2024-01-26 | 1 | bar: WEEK 4 T to WEEK 4 F
Update and integrate tablets with backend computer at main office |  | 2024-01-29 | 2024-01-29 | 0 | bar: WEEK 5 M
Hire electrician to install tablets on tabletop at two restaurants |  | 2024-01-30 | 2024-02-02 | 3 | bar: WEEK 5 T to WEEK 5 F
Test the running of new system at two restaurants |  | 2024-02-05 | 2024-02-08 | 3 | bar: WEEK 6 M to WEEK 6 T
Milestone: Train management and staff at North locations to use new tablets system |  |  |  | 0
Prepare training materials to use new tablets system |  | 2024-02-12 | 2024-02-13 | 1 | bar: WEEK 7 M to WEEK 7 T
Pre training meeting at North location for management |  | 2024-02-14 | 2024-02-14 | 0 | bar: WEEK 7 W
Seydou train and test manager at North location |  | 2024-02-15 | 2024-02-15 | 0 | bar: WEEK 7 T
Pre training meeting at North location for staff |  | 2024-02-16 | 2024-02-16 | 0 | bar: WEEK 7 F
Manager train and test front house staff at North location |  | 2024-02-19 | 2024-02-19 | 0 | bar: WEEK 8 M
Manager train and test back house staff at North location |  | 2024-02-20 | 2024-02-20 | 0 | bar: WEEK 8 T
Run a simulation of new system with selected guests at restaurant |  | 2024-02-21 | 2024-02-23 | 2 | bar: WEEK 8 W to WEEK 8 F
Milestone: Implement running of new tablet system at downtown restaurant |  |  |  | 0
Pre training material for using new tablets system |  | 2024-02-26 | 2024-02-26 | 0 | bar: WEEK 9 M
Pre taining meeting at Downtown for management |  | 2024-02-27 | 2024-02-27 | 0 | bar: WEEK 9 T
Seydou train and test manager at Downtown |  | 2024-02-28 | 2024-02-28 | 0 | bar: WEEK 9 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Procure Table
Work with GM from both locations to identify amount of tablets needed |  | 0 | 0 | 0 | 1 | H
Research for tablets options and prices with vendor |  | 0 | 0 | 0 | 1 | H
Create contracts and statement of work with vendor |  | 2 | 1 | 2 | 3 | H
Buy and receive the number of tablets |  | 10 | 7 | 10 | 14 | H
Milestone: Installation and setup
Develop internal training and policy for troubleshooting |  | 3 | 1 | 2 | 4 | M
Work with tablet vendor for common issues and turn around solving those |  | 2 | 1 | 2 | 4 | H
Hire an electrician to wire appropriate tablets on both location |  | 3 | 2 | 3 | 4 | M
Work with Carter for possible menu revamp |  | 10 | 4 | 10 | 14 | M
Milestone: Training
Develop training program and guide |  | 7 | 7 | 7 | 10 | H
Training meeting to introduce tablets |  | 1 | 1 | 1 | 2 | H
Work with GM's from both locations to schedule and hold meeting prior to roll out | Monitor staff response and possible question | 7 | 7 | 10 | 14 | L
Milestone: Test Run
Hold a test run by inviting friends and family event that mimics full service |  | 0 | 0 | 0 | 1 | H
Collect feedback from test run event |  | 1 | 0 | 1 | 4 | L
Meeting befor launch day and implement feedback from test run event |  | 3 | 2 | 1 | 4 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Customer want a faster, more efficient experience with correct orders | How satisfied are customers with the tablets? How does the use of tablets compare to other ordering methods in terms of satisfaction? | Customer satisfaction survey results, comparison of satisfaction ratings between tablet and other ordering methods. | TRUE
Training | Staff should be able to use the tablets effectively and efficiently. | How proficient are staff in using the tablets? How much time is being saved by using the tablets compared to traditional ordering methods? | Observation of staff using the tablets, timetracking data comparing tablet and traditional ordering methods. | TRUE
Tablet Hardware | Tablets should function properly and have minimal downtime. | How frequently do the tablets experience technical issues? How long does it take to resolve technical issues? | Number and duration of technical issues, time spent resolving technical issues | TRUE
Ease of use of the tablets | Customer should find the tablets easy to use | How easy do customers find it to place an order using the tablets? Do customers encounter any difficulties when using the tablets? | Customer survey results on ease of use, observations of customer interactions with the tablets. | TRUE
Productivity Enhancements | Tablets should improve efficiency and productivity in the restaurant. | How much time is being saved by using the tablets compared to traditional ordering methods? Are there any bottlenecks or inefficiencies in the ordering process that can be improved with the use of the tablets? | Time-tracking data comparing tablet and traditional ordering methods, observations of the ordering process with and without the tablets. | TRUE
Effectiveness | The tablets should be effective in meeting the goals of the project. | Have the tablets increase sale? Have the tablets improved the customer experience | Sales data before and after implementation of the tablets, customer feedback on the tablets | TRUE
Security | The tablets should be secure and protect customer data. | Have there been any security breaches or data leaks related to the tablets? | Number and severity of security breaches or data leaks | TRUE
User Experience | The tablet should have the positive user experience | How do they feel about using the tablets | Customer survey results on user experience, observations of customer interactions with the tablets. | TRUE
Intergration with POS system | The tablets should seamlessly integrate with the restaurant's point of sale system. | Are there any issues with the integration of the tablets and the POS system? How much time is being saved by using the tablets to input orders directly into the POS sys | Observations of the integration of the tablets and POS system, time-tracking data comparing input of orders through the tablets versus traditional methods. | TRUE
Cost-effectiveness | The tablets should be cost-effective and provide a good return on investment | What are the costs associated with implementing and maintaining the tablets? Are the tablets generating sufficient additional revenue to justify the costs? | Cost data for implementing and maintaining the tablets, revenue data before and after implementation of the tablets. | TRUE
Average ticketing time | the amount of time between placing an order and delivering it to the table | What is the average ticket time for orders placed through the tablets compared to traditional methods? Are there any bottlenecks or inefficiencies in the ordering and delivery process that can be improved with the use of the tablets? | Time-tracking data comparing ticket times for orders placed through the tablets versus traditional methods Observations of the ordering and delivery process with and without the tablets. | TRUE
Quicker Checkout | Target one-minute checkout time and ensure that the checkout process is seamless and easy to navigate from user perspective | What is the average checkout time for customers using the tablets compared to traditional methods? | Time-tracking data comparing checkout times for customers using the tablets versus traditional methods. | TRUE
Minimize reports of technical issues with tablets | Less than 5% of customers should reports technical issues each week | What is the percentage of customer reporting technical issues with the tablets each week? | Customers survey results on technical issues with the tablets | TRUE
Reduce incorrect orders | Target 98% accuracy | What is the percentage of correct orders placed through the tablets compared to traditional methods? | Data on the percentage of correct orders placed through the tablets versus traditional methods | TRUE
Decrease customers wait time in Lobby | Average wait time is 10 minutes or less before customers are seated | What is the average wait time for customers before being seated at the restaurant, with and without the use of the tablets for order placement? | Time-tracking data comparing wait times for customers with and without the use of tablets for order placement. | TRUE
Increase customers retention | Increase customers retention in tablets area by 5% | Have the tablets resulted in a 5% increase in customer retention in the tablet areas compared to non-tablet areas? | Comparison of customer retention data in tablet areas versus non-tablet areas before and after implementation of the tablets. | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5