## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | 40% of guests rated their experience as a 4 out of 5 | Data point from the survey | Continue to monitor customers satisfaction rating and work on improving the overall experience
Customers | Went well | 78% of customers signed up for the newsletter on the tablet | Data point from the survey | Analyze data to identify any trends or patterns in customer satisfaction rating
Customers | Went well | 40% of guests rated their experience as a 4 out of 5, 32% rated it as 5 out of 5 | Data point from the survey | Consider implementing additional training for staff to improve services and customer satisfaction
Customers | Needs improvement | The birthday clun did'nt get many participants | Data point from the survey | Work with the designer to update the content on the website and tablet to make the Birthday Club program more clear and accessible guests
Project team | Went well | The tablets were installed and working properly at both locations | "It seemed like all the guests got the hang of the tablets and that payments worked for the most part".-Gilly(General Manager, North) | None needed
Project team | Needs improvement | Table turn time remained about the same | "The food came out on time, but table turn time stayed about the same" -Alex(General Manager, Downtown) | Review and analyze data to identify potential causes of slow table turn time and brainstorm solutions. Implement any necessary improvements to table turn time processes.
Project team | Needs improvement | There wew still some food orders that got sent back | "Even thought the ticket flow was smooth, there were still orders that got sent back" -Zane(Kitchen Manager, North) | Review and analyze data to identify potential causes of incorrect food orders and brainstorm solutions. Implement any necessary improvements to kitchen operations and processes.
Project team | Needs improvement | Some internal operational issues wew discovered during the training process | "As we started implementing the tablets and training, we discovered a few internal operational issues that we hadn't planned for. That impacted the team's ability to carry out tasks smoothly." -Peta | Research and understand each location's history before planning future rollouts to identify potential issues that may need to be addressed ahead of time.
Project team | Needs improvement | Tablet implementation took longer than expected | "Tablet implementation took just a little bit longer than we hoped. There was some vacation time that was unaccounted for, so this is a good reminder to make sure we plan things properly based on everyone's availability." -Seydou(Restaurant Consulted) | Review and adjust project planning to account for vacation time and other potential scheduling conflicts.
Project team | Needs improvement | Back of the house staff needs more preparation for scaling up operations. | "We'd like to do a bit more to help the back of house staff sale up their operations before the main launch. We want everyone to be prepared to handle a larger volume of orders." -Zane(Kitchen Manager, North) | Review and analyze data to identify potential areas of improvement for scaling up operations. Implement any necessary changes to processes and procedures.
Project team | Needs improvement | Front of house and back of house staff have a lack of understanding of each other's roles and responsibilities. | "We also noticed there's a lack of understanding between what the front of house staff does and the back of house staff does." -Larissa(Kitchen Manager, Downtown) | Implement training or team building activites to improve communication and understanding between front of house and back of house staff.