## Slide 1: Tablet Test Launch Presentation

## Slide 2
Summary
Sauce & Spoon successfully completed the pilot launch of tablets at two locations in the bar area of each restaurants:
  Sauce & Spoon North
  Sauce & Spoon Downtown
The project team worked closely with vendors to customize and brand the tablets, and trained staff on their use.
We gathered valuable customer feedback & data on the performance of the tablets in a real-world setting
We integrated the tablets successfully with the restaurant’s POS system and smoothly rolled out the tablets to customers.

## Slide 3
Overview
The team wanted to measure the effectiveness of the tablets in terms of customer satisfaction, ease of use, and productivity enhancements.
We conducted a survey with 50 guests who dined with us and used the tablets during their visit.
The survey consisted of multiple choice, scaled and open-ended questions that allowed us to gather data on various aspects of the tablet rollout.
Evaluation questions included.
  “On a scale of 1-5, please rate your experience with the tablet overall”
  “How easy was it to use the tablet navigation?”
  “On a average, how long did you wait for your table?”

## Slide 4
Findings
Overall, the tablets received a rating of 3.8 out of 5 for customer satisfaction.
  40% of respondents rated their overall experience with the tablets as “great” (rating of 5 out of 5), while 32% rated their experience as “neutral” (rating of 3 out of 5)
82% of respondents ordered appetizers, while only 70% ordered dessert, indicating that the tablets may be more popular for ordering food rather than drinks or dessert.
80% rated the ease of tablet navigation as either 4 or 5 out of 5.
The average wait time for a table was 13 minutes.

## Slide 5
Next Steps
One recommendation for improvement is to focus on reducing the wait time for a table.
  This could be achieved by increasing the number of tablets available for use, or streamlining the table reservation process.

## Slide 6
Next Steps
Optimize the tablet navigation for ease of use.
  This could include more user testing and design updates to make the interface more intuitive for customers.
  The team should also consider offering additional training for waitstaff on how to troubleshoot and resolve any technical issues that may arise with the tablets.